## Q2 2026
Project Review Checklist
Project Name | [5 empty] | Billing Type
Project ID | [5 empty] | Project Manager
Project Start Date | [5 empty] | Project State/Phase
Project End Date | [5 empty] | Review Date
Project Type | [5 empty] | Participants
|  |  |  | Compliance Status | #DIV/0!
Sr. No. | Phases/Process | Activities | Checkpoint |  |  |  | Response | Weighted | Score | Weighted Score | Average Score | observation | Formulas:
1 | Initiation | SOW | Signed SOW is available |  |  |  |  | 5 |  |  |  |  | Count of NO | 0
|  |  | Approved SOW is available |  |  |  |  | 5
|  |  | SOW reviewed and understood by key stakeholders |  |  |  |  | 4
|  |  | Scope of work is clearly defined in SOW |  |  |  |  | 5 |  |  |  |  | Count of Yes | 0
|  |  | Scope of work defined including inclusions and exclusions (In scope/Out Scope) |  |  |  |  | 5
|  |  | Deliverables Identified in SOW (Statement) |  |  |  |  | 4 |  |  |  |  | Total applicable checkpoints | 0 | Div | #DIV/0!
|  |  | Project timelines/milestones defined in the SOW |  |  |  |  | 4
|  |  | Acceptance criteria for deliverables defined |  |  |  |  | 5
|  |  | Required skills identified for the project |  |  |  |  | 3
|  |  | Timelines of a invoices defined |  |  |  |  | 2
|  |  | Dependencies tracked to closure |  |  |  |  | 3
|  | Lifecycle identification | Lifecycle identified for the project |  |  |  |  | 4
|  |  | Execution methodology identified (Agile/Waterfall/Hybrid) |  |  |  |  | 4
|  |  | Selected methodology formally approved and documented by key stakeholders |  |  |  |  | 5
|  |  | Milestones / Schedule / High-level Sprint Plan defined |  |  |  |  | 5
|  | Estimation Approval | High Level Estimations available |  |  |  |  | 5
|  |  | Acceptance on the estimation available |  |  |  |  | 5
|  |  | Detailed estimations available for all tasks/deliverables |  |  |  |  | 5
|  |  | Estimation technique/methodology defined and documented |  |  |  |  | 4
|  |  | Changes in estimations communicated to stakeholders and approved |  |  |  |  | 4
|  |  | Estimation available in JIRA Tool (Confluence) |  |  |  |  | 2
|  |  | Estimation changes logged and tracked |  |  |  |  | 3
|  |  | Contingency included in estimation |  |  |  |  | 4
|  | Team Allocation | Team request raised and approved |  |  |  |  | 5
|  |  | Team allocated to the project (number of resources confirmed) |  |  |  |  | 5
|  |  | Project Buffers allocated to the project |  |  |  |  | 3
|  |  | Roles and responsibilities communicated to all team members |  |  |  |  | 5
|  |  | Team members onboarded with required system/access rights |  |  |  |  | 5
|  |  | Team performance monitoring process defined |  |  |  |  | 3
|  |  | Backup/reserve resources identified |  |  |  |  | 2
|  |  | Skill gaps identified and training planned |  |  |  |  | 3
|  |  | Trainings based on skills planned and executed |  |  |  |  | 3
|  | Kick-off | Kick-off conducted for the project |  |  |  |  | 5
|  |  | Kick-off meeting conducted with all relevant team members |  |  |  |  | 5
|  |  | Minutes of Meeting (MOM) for kick-off shared with all relevant stakeholders |  |  |  |  | 3
|  |  | Presentation and attendance record available |  |  |  |  | 2
|  |  | Project objectives, scope, and execution approach discussed |  |  |  |  | 5
|  |  | Communication plan and reporting structure shared |  |  |  |  | 4
|  |  | Initial risks and assumptions discussed |  |  |  |  | 3
2 | ERP | ERP Setup | Project clearly created in ERP system with correct start/end dates |  |  |  |  | 5
|  |  | Resources allocated to the project in ERP and roles assigned |  |  |  |  | 5
|  |  | Resource percentage allocation correctly reflected in ERP |  |  |  |  | 4
3 | Project Planning | Project Plan Communication | Project Plan document created (CM, RSKM, Communication, Resource, Metrics/SLA) |  |  |  |  | 5
|  |  | PMP document approved and version-controlled |  |  |  |  | 5
|  |  | Project Plan shared with the team to understand execution methodology |  |  |  |  | 4
|  |  | Resource plan developed |  |  |  |  | 5
|  |  | Communication plan agreed and informed to all stakeholders |  |  |  |  | 4
|  |  | Escalation process defined and communicated |  |  |  |  | 3
|  |  | Service Level Agreement (SLA) defined and documented for project |  |  |  |  | 5
|  |  | Tools/Access to system / Required Infra available |  |  |  |  | 5
|  |  | Stakeholder sign-off on project plan obtained |  |  |  |  | 5
|  |  | Access request for the team members of Tools/System |  |  |  |  | 3
4 | Requirement Management | Requirement Gathering | Methods of requirement gathering defined (interviews, workshops, surveys, etc.) |  |  |  |  | 5
|  |  | Requirement received from client to the team in any format (Staff-Aug ) |  |  |  |  | 5
|  |  | BRD/ Product Backlog Created |  |  |  |  | 5
|  |  | Use cases and user story defined |  |  |  |  | 5
|  |  | Functional and Non-Functional Requirements called out |  |  |  |  | 5
|  |  | Requirements approved by client SPOC |  |  |  |  | 5
|  |  | Definition of Done/ Acceptance criteria for requirements established |  |  |  |  | 5
|  |  | Requirement traceability matrix (RTM) created |  |  |  |  | 4
|  |  | Prioritization of requirements(Medium, Low , High) |  |  |  |  | 4
|  |  | Requirement Understanding established in the team |  |  |  |  | 5
|  |  | Security Requirements identified (Coding and Test Data) |  |  |  |  | 4
|  |  | If the project is related to the Personally Identification information(PII) |  |  |  |  | 2
|  |  | PII Included in a Project |  |  |  |  | 3
88
5 | Design | Design | High Level Design Created |  |  |  |  | 5
|  |  | Low Level Design Created |  |  |  |  | 5
|  |  | Prototype/wireframe created(Figma/Lucid chart) |  |  |  |  | 3
|  |  | Mockups or screen designs reviewed with stakeholders(Client) |  |  |  |  | 3
|  |  | Design covers all functional and non-functional requirements |  |  |  |  | 5
|  |  | Security controls addressed in design documentation |  |  |  |  | 5
|  |  | Design document versions tracked and maintained |  |  |  |  | 3
|  |  | Technical documentation created (architecture diagrams, database schemas, interfaces) |  |  |  |  | 5
|  |  | Client approvals obtained for HLD and LLD documents - Technical Documents |  |  |  |  | 5
6 | Sprint Execution | Sprint Planning meeting | Team capacity planning done before each sprint |  |  |  |  | 5
|  |  | Sprint goals defined and communicated to the team |  |  |  |  | 5
|  |  | Sprint Plan created in JIRA |  |  |  |  | 3
|  |  | Sprint Backlog Created |  |  |  |  | 5
|  |  | User stories estimated and sized (Story Points / Hours / Days) |  |  |  |  | 3
|  |  | Size of user stories definition defined (for Agile) - Small,Medium,Large |  |  |  |  | 5
|  |  | Acceptance criteria for user stories clearly defined |  |  |  |  | 5
|  |  | Issues and dependencies identified |  |  |  |  | 4
|  |  | Stories broken down into actionable tasks |  |  |  |  | 4
|  |  | Task allocated to the team members |  |  |  |  | 5
|  |  | Sprint Planning Meeting conducted with all team members (developers, testers, scrum master, product owner) |  |  |  |  | 4
|  | Sprint Execution | Sprint backlog reviewed and accepted by Product Owner |  |  |  |  | 5
|  |  | Work progress monitored against sprint goals |  |  |  |  | 5
|  |  | Bottlenecks or blockers identified and discussed during daily stand-ups |  |  |  |  | 4
|  |  | Task progress updated in project management tool |  |  |  |  | 3
|  |  | Demo done at the end of the sprint |  |  |  |  | 4
|  | Sprint Closure | All planned sprint tasks/stories completed |  |  |  |  | 5
|  |  | Incomplete user stories documented for next sprint |  |  |  |  | 5
|  |  | Dependencies for next sprint identified and communicated |  |  |  |  | 4
|  |  | Sprint metrics (task baords, velocity, burn-down graphs) updated |  |  |  |  | 3
|  |  | Retrospective conducted and improvement actions identified |  |  |  |  | 4
|  |  | Action items from retrospectives tracked to closure |  |  |  |  | 4
|  |  | Confirmation that all team members are aware of closure and next sprint planning |  |  |  |  | 3
7 | Execution | Deliverables Communication | Deliverables expected for the project communicated to the team |  |  |  |  | 5
|  |  | Deliverables tracking mechanism in place (JIRA, Excel) |  |  |  |  | 4
|  |  | Any changes or updates to deliverables communicated promptly |  |  |  |  | 5
8 | Coding | Code Quality & Standards | Coding standards established and followed |  |  |  |  | 5
|  |  | Secure coding practices followed |  |  |  |  | 5
|  |  | Code reviews conducted by (Name) |  |  |  |  | 4
|  |  | Code reviews conducted before check-in or merge |  |  |  |  | 5
|  |  | Code review comments tracked and closed |  |  |  |  | 4
|  |  | Code quality issues identified, reviewed, and resolved |  |  |  |  | 5
|  | Code Testing | Unit test cases created |  |  |  |  | 5
|  |  | Unit test cases executed |  |  |  |  | 5
|  |  | Code coverage metrics maintained |  |  |  |  | 4
|  |  | Unit Tests results validated |  |  |  |  | 5
|  |  | UT created for every Commit |  |  |  |  | 4
|  |  | Defects found in UT tracked to closure(Optional) |  |  |  |  | 3
9 | Testing | Testing | Test plan Created |  |  |  |  | 5
|  |  | Test plan reviewed and approved by manager/Client |  |  |  |  | 5
|  |  | Types of testing identified: Functional, Non-Functional, Smoke, Regression, UAT, Performance, Security and Load |  |  |  |  | 4
|  |  | Detailed test cases created for all requirements |  |  |  |  | 5
|  |  | Test Cases reviewed by QA Manager |  |  |  |  | 5
|  |  | Test Cases approved/agreed by Client |  |  |  |  | 5
|  |  | Automation test scripts created |  |  |  |  | 4
|  |  | Test cases executed as per the test plan |  |  |  |  | 5
|  |  | Integration testing executed |  |  |  |  | 5
|  |  | Functional testing executed |  |  |  |  | 4
|  |  | Non-functional testing executed (Regression/Sanity / Performance/Security/Load testing) |  |  |  |  | 4
|  |  | Sanity testing performed after bug fixes |  |  |  |  | 5
|  |  | Defect related metrics tracked |  |  |  |  | 3
|  |  | Test reports generated |  |  |  |  | 4
|  |  | Test Summary Report created and shared with stakeholder |  |  |  |  | 4
|  | Defect Management | Defects identified during testing |  |  |  |  | 5
|  |  | Defects raised against failed test cases |  |  |  |  | 5
|  |  | Defect logged in a defect tracking tool (JIRA, Azure DevOps, Bugzilla) |  |  |  |  | 5
|  |  | Defects assigned to the relevant team members |  |  |  |  | 4
|  |  | Defect resolution status tracked and updated in tool (Open → In Progress → Fixed → Verified → Closed) |  |  |  |  | 5
|  |  | Complete defect lifecycle followed – Raise, Log, Prioritize, Assign, Fix, Retest, Close, Analyze, Improve. |  |  |  |  | 5
|  |  | Defects summary report created and shared with stakeholder |  |  |  |  | 4
|  | UAT | UAT Test cases Identified |  |  |  |  | 5
|  |  | UAT Test cases reviewed and approved by client |  |  |  |  | 5
|  |  | UAT executed as per test plan |  |  |  |  | 5
|  |  | Defects/issues logged during UAT |  |  |  |  | 5
|  |  | UAT execution results and communicated to relevant team |  |  |  |  | 4
|  |  | UAT sign-off received from business/client |  |  |  |  | 5
10 |  | Security Testing | Vulnerability and penetration test results recorded |  |  |  |  | 4
11 | Release | Pre- Release
|  |  | Completed all planned development tasks |  |  |  |  | 5
|  |  | Code reviewed comments closed |  |  |  |  | 5
|  |  | Code merged into main/release branch |  |  |  |  | 5
|  |  | Unit test cases passed |  |  |  |  | 5
|  |  | All test cases passed and defects closed |  |  |  |  | 5
12 | Deployment | Pre-production | Deployment to staging environment completed |  |  |  |  | 5
|  |  | Smoke testing / basic functionality checks executed |  |  |  |  | 5
|  |  | Confirm database and configuration updates |  |  |  |  | 5
|  |  | Created and share release notes for every production release |  |  |  |  | 4
|  |  | User guide and knowledge base updated |  |  |  |  | 4
|  |  | Conducted release-related calls/meetings with stakeholders |  |  |  |  | 3
|  | Production Deployment | Deploy the new release to production |  |  |  |  | 5
|  |  | Sanity checks performed post-production deployment |  |  |  |  | 5
|  |  | Release communicated to users/stakeholders |  |  |  |  | 4
|  |  | Handover session for client planned for the release |  |  |  |  | 4
|  |  | Deliverables verified against release plan |  |  |  |  | 5
|  |  | Acceptance on Deliverables/Released Product available |  |  |  |  | 5
13 | Monitoring | Communication | Meetings planned as per Communication Plan |  |  |  |  | 5
|  |  | MOM created and shared for relevant meetings |  |  |  |  | 5
|  |  | Action items from all the MOM are being tracked to closure |  |  |  |  | 5
|  |  | Dependencies identified and communicated |  |  |  |  | 4
|  |  | Dependencies tracked to closure |  |  |  |  | 5
14 | Client Reporting | Weekly/Monthly | Weekly Status Report prepared |  |  |  |  | 5
|  |  | Weekly Status Report shared with client |  |  |  |  | 5
|  |  | WSR reviewed before sharing |  |  |  |  | 4
|  |  | Risks/issues for the week updated and communicated |  |  |  |  | 5
|  |  | Monthly Status Review meeting Done |  |  |  |  | 5
|  |  | MOM for Monthly Status meeting shared |  |  |  |  | 4
|  |  | Monthly Status Report shared with client |  |  |  |  | 5
|  | Quarterly Activities | QBR Meeting Conducted |  |  |  |  | 5
|  |  | Quarterly Report shared |  |  |  |  | 5
|  |  | MOM for Quarterly meeting shared |  |  |  |  | 4
|  |  | Client feedback from QBR captured and documented(Action Item) |  |  |  |  | 5
|  | Client Communication | Escalation matrix defined and shared |  |  |  |  | 5
|  |  | Risks and mitigation plans communicated to the client |  |  |  |  | 5
|  |  | Project KPIs / performance metrics reviewed with the client |  |  |  |  | 5
|  |  | Client feedback or acknowledgment received |  |  |  |  | 4
|  |  | Changes communicated to the client and agreed upon (WSR,MSR) |  |  |  |  | 5
15 | Internal Monitoring | Performance Tracking | Monthly Dashboard (MSR) Created |  |  |  |  | 5
|  |  | Monthly Dashboard (MSR) Reviewed (Director) |  |  |  |  | 5
|  |  | Monthly Dashboard (MSR) shared with SEPG |  |  |  |  | 4
|  |  | Daily Stand Up meetings conducted |  |  |  |  | 5
|  |  | Impediments tracking done |  |  |  |  | 5
|  |  | Lesson Learned/ What went well/ Areas to improve recorded and tracked |  |  |  |  | 4
|  |  | Appreciations/Concerns collected from the client |  |  |  |  | 4
16 | Risk Management | Planning and Documentation | Risk Management Plan Established |  |  |  |  | 5
|  |  | Risk mitigation and contingency identified |  |  |  |  | 5
|  |  | Risk Register Created and maintained |  |  |  |  | 5
|  |  | Risk owners / responsible persons assigned for each risk |  |  |  |  | 5
|  |  | Risk priority identified - High , Medium, Low |  |  |  |  | 4
|  |  | Risks communicated as part of Meetings/MOM |  |  |  |  | 4
|  | Monitoring and Communication | Risk are monitored regularly |  |  |  |  | 5
|  |  | Risks communicated timely to all stakeholders |  |  |  |  | 5
|  |  | Escalation triggered for critical risks |  |  |  |  | 5
|  |  | Risk status updated regularly (Open / Mitigated / Closed) |  |  |  |  | 5
|  |  | Risk dashboard or report shared periodically |  |  |  |  | 4
|  | Review and Closure | Risks reviewed in scheduled project meetings |  |  |  |  | 5
|  |  | Lesson learned from risk management documented |  |  |  |  | 4
17 | Project Metrics | Metrics | Metrics for the project are identified and clearly defined |  |  |  |  | 5
|  |  | Metrics are communicated to stakeholders |  |  |  |  | 4
|  |  | Metrics are being captured |  |  |  |  | 5
|  |  | Metrics data is being analyzed |  |  |  |  | 5
18 | Change management | Change control | Change Management process defined for the project |  |  |  |  | 5
|  |  | Change Requests created as per defined format |  |  |  |  | 5
|  |  | Change Log created and maintained |  |  |  |  | 5
|  |  | Impact analysis done for each change request |  |  |  |  | 5
|  |  | Approvals on CR's available |  |  |  |  | 5
|  |  | Verification and validation post-implementation of changes |  |  |  |  | 5
|  |  | Lessons learned from change captured |  |  |  |  | 4
|  | Changes in Team | Deactivation records for offboarding team members |  |  |  |  | 5
|  |  | Access revoked across all systems (VPN, Git, servers, trackers, email) |  |  |  |  | 5
|  |  | Handover of tasks/work items completed and reviewed |  |  |  |  | 5
|  |  | Project asset return confirmed(Laptops, ID Badges, Security devices) |  |  |  |  | 5
|  |  | Activation Record for onboarding replacement team members |  |  |  |  | 5
|  |  | Access provisioning completed (tools, systems, repositories, emails) |  |  |  |  | 5
|  | Knowledge Transfer (KT) | KT for new Onboarding Resource |  |  |  |  | 5
|  |  | Reverse KT conducted for the new team member |  |  |  |  | 4
|  |  | KT Session documented and shared |  |  |  |  | 4
19 | Incident management | Logging and Resolution | Incident Log Created |  |  |  |  | 5
|  |  | Incident Communicated to all required stakeholders |  |  |  |  | 4
|  |  | Corrective Actions Identified |  |  |  |  | 5
|  |  | Incidents Tracked to Closure |  |  |  |  | 5
|  | Communication Management | Client calls conducted as per communication plan |  |  |  |  | 5
|  |  | Escalation matrix defined and shared |  |  |  |  | 5
|  |  | Risks and mitigation plans communicated to client |  |  |  |  | 4
20 | Commercials | Billing & Tracking | Invoices raised as per SOW |  |  |  |  | 5
|  |  | Payment terms adhered to for all invoices |  |  |  |  | 5
|  |  | Billing/Invoices status shared with the client |  |  |  |  | 4
|  |  | Commercials tracked for the project |  |  |  |  | 5
|  |  | All raised invoices cleared |  |  |  |  | 5
|  |  | If the payment is in INR (GST 18 %) Included or not |  |  |  |  | 4
21 | Review/Audit | Issue Resolution | Audit conducted for the Project |  |  |  |  | 5
|  |  | RCA Conducted for the findings |  |  |  |  | 5
|  |  | Action taken and status updated for the findings |  |  |  |  | 5
|  |  | Action plan Submitted on Time |  |  |  |  | 4
|  |  | Re-audit or follow-up audit conducted where required (For Project) |  |  |  |  | 4
22 | Closure | Project Closure | Project Closure Report prepared |  |  |  |  | 5
|  |  | Resources Released |  |  |  |  | 5
|  |  | Skills updated |  |  |  |  | 4
|  |  | Risks Shared with SEPG |  |  |  |  | 4
|  |  | Lesson Learned Shared |  |  |  |  | 4
|  |  | Closure officially signed off |  |  |  |  | 5
|  |  | Acceptance received from client |  |  |  |  | 5
23 | Project Specific Checkpoints | CAM | Capacity Planning done |  |  |  |  | 5
|  | SCON | Business Continuity Planned and executed |  |  |  |  | 4
|  | DAR | Any Major decision or tool change |  |  |  |  | 5
|  | SST | Transitions planned and executed |  |  |  |  | 4
Total Compliance Percentage

## Findings
Project Review Checklist - Staff Aug Projects
Project Name |  |  |  |  | Billing Type
Project ID |  |  |  |  | Project Manager
Project Start Date |  |  |  |  | Project State/Phase
Project End Date |  |  |  |  | Review Date
Project Type |  |  |  |  | Participants
Compliance Status
Sr. No. | Date of Audit | Category | Finding | Area | Details | Cause | Correction | Prevention | Status | Closed Date | Closure Comments | Column1

## Transcript
Transcript